## User Stories Master
User Stories
ID | User Story | Business Value | Acceptance Criteria | Priority | Status | Story Points | Sprint | Owner
US-1 | As an eCommerce Manager, I want new orders from the website to be automatically created in the ERP, so that we eliminate manual data entry and fulfill orders faster. | Reduce manual work & faster fulfillment | When order is placed, sync runs and sales order is created in ERP with correct details. | High | To Do | 8 | TBD | Dev Lead 1
US-2 | As a Registered Customer, I want to see my special negotiated prices when I log into the eCommerce store, so that I can purchase at my correct pricing. | Pricing accuracy & customer trust | Logged-in customer sees custom pricing applied across site including cart & checkout. | High | To Do | 5 | TBD | Dev Lead 2
US-3 | As a Sales Manager, I want notifications for orders over $10,000 so that I can approve before processing. | Approval control on high-value orders | Order over $10k triggers email and moves order to approval queue. | High | To Do | 3 | TBD | Dev Lead 3
US-4 | As an eCommerce Manager, I want a report of the top 10 selling products last month for marketing and inventory planning. | Data-driven business decisions | Auto-generated on 1st of month with top products by revenue, visible in admin. | Medium | To Do | 8 | TBD | BI Team
US-5 | As a System Administrator, I want logs of sync activities & errors to troubleshoot issues quickly. | Faster issue resolution | Logs created for each sync with timestamps & record IDs. | Medium | To Do | 3 | TBD | DevOps

## Automation Test Cases
Automation Test Cases
Test Case ID | Related US | Test Scenario | Test Steps | Expected Results | Automation | Pass/Fail
TC-US1-01 | US-1 | Verify web orders sync to ERP automatically | Place order on website > Run sync job > Check ERP system | Order appears in ERP with correct details | Yes | TBD
TC-US2-01 | US-2 | Verify special pricing updates for registered customer after login | Login with special pricing account > Check product list | Prices update correctly for user | Yes | TBD
TC-US3-01 | US-3 | Verify notification for high value orders | Place order > $10k > Check email + approval queue | System sends email + approval status updated | Yes | TBD
TC-US4-01 | US-4 | Verify system generates top 10 product report on 1st of month | Check admin panel on 1st > Validate report | Report visible with correct products sorted by revenue | Partial | TBD
TC-US5-01 | US-5 | Verify logging of sync activity & errors | Trigger sync job > Check logs recorded | Logs captured with timestamp and details | Yes | TBD

## Traceability Matrix
Traceability Matrix
User Story ID | Business Requirement | Test Case ID(s) | Status
US-1 | BR-1 | TC-US1-01 | To Be Tested
US-2 | BR-2 | TC-US2-01 | To Be Tested
US-3 | BR-3 | TC-US3-01 | To Be Tested
US-4 | BR-4 | TC-US4-01 | To Be Tested
US-5 | BR-5 | TC-US5-01 | To Be Tested

## Data Mapping
Data Mapping
eCommerce Field | ERP Field | Data Type | Sample Value | Transformation / Notes
order_id | ExternalOrderID | Text | "WEB-10025" | Prefix added for traceability.
order_date | OrderDate | Date/Time | "2023-10-27 14:30:00" | Format must be converted to ERP standard.
customer_email | CustomerEmail | Text | "john.doe@email.com" | Used to match existing customer in ERP.
billing_address.first_name | BillToAddress.FirstName | Text | "John"
billing_address.last_name | BillToAddress.LastName | Text | "Doe"
grand_total | TotalAmount | Decimal | 250.99
status | Status | Text | "Approved" | Mapped from eCommerce status (e.g., 'processing') to ERP status (e.g., 'Approved').

## Gap Identification
Gap Identification
Gap ID | Area / Feature | Clarification Question for the Client
G-1 | High-Value Order Threshold | What is the exact monetary threshold that defines a "high-value" order? Is this threshold global, or can it vary by customer group or region?
G-2 | Error Handling & Alerts | For a failed order sync (e.g., ERP is down), how many times should the system retry, and at what intervals? Who should be alerted (email/SMS) for critical failures?
G-3 | Product & Inventory Sync Scope | Should the integration sync all products or only those marked as "active" or "web-enabled"? For inventory, should we sync all warehouse quantities or only a specific "available-to-sell" quantity?